## Sheet1
Approximated Timeframe for Completion | Activity. Mandated activities with no statutory date are in red and scheduled dates are suggestions from SOS. Activities to be completed on specific statutory dates have their cells filled in with yellow.
1 Month: To be completed simultaneously with outreach to groups, advocates, stakeholders and officials. | Begin coordinated research effort with SOS support to identify and provide training to community groups, advocates, stakeholders, and officials that should participate in the public workshop process. (1 month development time)
3 Months: To be completed prior to the public workshopping period for the Election Administration Plan (EAP) | Begin outreach and provide training to community groups, advocates, stakeholders, and officials to ensure broad participation in a public workshop process. (3 month training and outreach period)
2 Months: To be completed simultaneously with outreach to community groups and prior to public workshops on EAP | Begin internal Election Administration Plan (EAP) development (2 month development window prior to public input workshops).
- | Deadline for internal EAP development process. This ensures a proper working skeleton draft of an EAP that can be presented and workshopped with community groups.
10 days prior to planned public workshops | Begin issuance of public notice for workshops on EAP.
- | Deadline for outreach to community groups, advocates, stakeholders, and officials.
3 weeks: Concentrated schedule of workshops on EAP to get feedback prior to issuing the draft EAP for public hearing | Beging public workshop period. At least one meeting with…
3 weeks: Update EAP skeleton plan as you receive public input during the workshopping period | End public workshop period.
14 days: Public comment period prior to public hearing on draft EAP | Publish proposed Election Administration Plan (EAP). Begin 14-day public comment period on proposed EAP.
10 days | Issue 10-day public notice of hearing to consider proposed EAP if using suggested plan development dates.
1 day (It is suggested you start here and work backwards and forwards from this date to generate your ideal calendar) | Public hearing to consider proposed EAP (one week to amend plan after hearing).
1 week | Date to publish amended EAP after hearing. Begin 14-day public comment period on published amended EAP.
14 days: Public comment period for revised EAP | Date to adopt final amended plan and send outreach plan to SOS for approval.
14 days: period for SOS staff to review submitted outreach plan | SOS deadline for approval of outreach plan if using suggested dates for EAP development.
2017-10-01 | Deadline to establish county VAAC/LAAC.
3 months: Materials to be developed for launch of the public outreach portion of the EAP | Develop voter outreach and education materials, PSA development, newspaper announcements and media plans, and other documents or materials for activities in approved outreach plan (3 months of materials development). Coordinate with SOS regarding available materials from SOS office.
6 months: Execution of all of the activities included in the public outreach plan | Begin voter outreach and education activities. Activities include items detailed in the SOS approved outreach plan including social media engagement, traditional media for english and other required language communities, required PSAs, and other public education activities.
3 month hiring and training window for new SB450 related staff | Beginning of period to recruit and hire needed temporary vote center staff. (3 month hiring window with staff starting May 1)
Feb 5 2018 | Deadline for amendments to an election administration plan.
Mar 7 2018 | Last possible day for public comment if EAP was amended on the last day allowed by law.
First of two direct contact with voters regarding new election administration should probably not be earlier than 3 months out | First direct (mailer?) contact with voters regarding the change in election administration.
1 day (Mar 9 2018) | Determination of the number of registered voters in the county in order to determine the number of vote centers and drop boxes required.
1 day (Apr 1 2018) [though it is highly recommended that your advisory committees meet at least once prior to the EAP amendments deadline (Feb 5, 2018)] | Latest date for a county VAAC/LAAC to hold their first meeting
Second of two direct contacts with voters about new election administration should probably not be earlier than 2 months out from election | Second direct (mailer?) contact with voters regarding the change in election adminstration. Also, publish the list of vote center and ballot drop of locations and hours.
1 month: Period to complete all required accesibility and language community public education meetings. One meeting with general public education is also highly recommended | Begin completing required language and disability workshops. One bilingual workshop for each language community served and one to increase accesss and participation for voters with disabilities. It may also be useful to host one or more general information workshops for the general public regarding the changes in voting administration. Consider using connections with community organizations to provide widespread outreach to community.
- | Deadline to finalize hiring of any temporary vote center staff.
1 month: Train and coordinate staff activities for new vote centers | Period to begin training for vote center staff.
- | End public workshops period.
1 month (May 7 2018) | Vote by mail ballot packets must be mailed to each voter by this date. Toll-free voter assitance hotlines must be operational.
1 month (May 8 2018) | Ballot dropoff locations required to be open during regular business hours. One must be available at least 12 hours per day.
1 month | Ballot dropoff location management activities begin.
10 days (May 26 2018) | Vote Centers (1 per 50k, minimum of 2) must be open for at least 8 hours per day
7 days (May 29 2018) | VBM Language and Accessibility ballot request deadline.
3 days (Jun 2 2018) | Vote centers (1 per 10k) must open for at least 8 hours per day.
June 5 2018 | ELECTION DAY